ScanWell CRM

AI Integration — Project Timeline

| Version | 1.0 | Date | April 2, 2026 |
| --- | --- | --- | --- |
| Project Start | April 14, 2026 | Target Completion | September 5, 2026 |
| Duration | 20 Weeks (5 Months) |  |  |

1.  Project Timeline Overview

The AI integration project is planned across five phases over a 20-week period. Each phase corresponds to a deliverable milestone with a client review checkpoint. The project follows an iterative delivery model to ensure continuous alignment with business needs.

2.  Project Phases

Phase 1: Discovery & Architecture  —  Weeks 1–2  |  April 14 – April 25, 2026

Activities:

- Codebase audit and AI integration feasibility assessment

- Review historical data availability for lead scoring and forecasting models

- Define data schemas for AI model inputs and outputs

- Finalise technical architecture: API endpoints, React component structure, AI provider configuration

- Set up Claude API account and development environment

- Establish Git branching strategy for AI feature development

Deliverables:

- Technical Architecture Document

- AI Integration Design Specification

- Development environment ready

Milestone Review: April 25, 2026

Phase 2: Core AI Infrastructure & Lead Scoring  —  Weeks 3–6  |  April 28 – May 23, 2026

Activities:

- Build AI service layer in .NET backend (new AIController and AI service classes)

- Integrate Claude API into backend for NLP tasks

- Develop lead scoring algorithm using historical lead and conversion data

- Build scoring model training/update pipeline

- Integrate lead scores into Lead Management module (frontend)

- Implement visual priority indicators and sort-by-score functionality

- Unit testing and code review

Deliverables:

- AI Service Layer (Backend)

- Lead Scoring Engine

- Updated Leads Module with AI scoring UI

Milestone Review: May 23, 2026

Phase 3: Quote Recommendations & Smart Documents  —  Weeks 7–11  |  May 26 – June 27, 2026

Activities:

- Develop historical rate analysis engine from existing quote and rates data

- Build recommendation panel component (React) for quote creation forms

- Implement auto-fill and anomaly detection for quote rates

- Develop AI-assisted PDF generation for quotes and invoices

- Implement email draft generation using Claude API with CRM context injection

- Add “Generate with AI” buttons to Quote and Invoice modules

- Integration testing across quote modes (Direct, Transit, Warehouse)

Deliverables:

- Quote Recommendation Engine

- Smart Document Generation Feature

- AI-Enhanced Quote and Invoice Modules

Milestone Review: June 27, 2026

Phase 4: Sales Forecasting Dashboard & AI Assistant  —  Weeks 12–17  |  June 30 – August 8, 2026

Activities:

- Build statistical forecasting model using pipeline and closed deal data

- Develop AI Insights section within the Reports module

- Implement monthly/quarterly trend charts and target attainment indicators

- Design and build AI Assistant chat interface component

- Implement CRM data query resolution (natural language to SQL/API calls)

- Integrate AI Assistant panel into application shell (accessible from all modules)

- End-to-end integration testing of all AI features together

Deliverables:

- AI Sales Forecasting Dashboard

- Internal AI Assistant (Chat Interface)

- Full AI Feature Integration

Milestone Review: August 8, 2026

Phase 5: UAT, Refinement & Deployment  —  Weeks 18–20  |  August 11 – September 5, 2026

Activities:

- User Acceptance Testing (UAT) with client stakeholders across all five AI features

- Bug fixes and performance optimisations based on UAT feedback

- Security review and penetration testing of new AI endpoints

- Production deployment to https://crm.scanwellapps.com

- Post-deployment smoke testing

- Handover documentation and knowledge transfer

- Final project sign-off

Deliverables:

- UAT Sign-Off Report

- Production Deployment

- Technical Handover Documentation

- Final Project Closure Report

Milestone Review: September 5, 2026 (Final Sign-Off)

3.  Milestone Summary

|  | Milestone | Description | Date |
| --- | --- | --- | --- |
| M1 | Architecture Complete | Technical design finalised, dev environment ready | Apr 25, 2026 |
| M2 | Lead Scoring Live | AI scoring integrated into Leads module | May 23, 2026 |
| M3 | Quote & Document AI Live | Recommendation engine and smart generation deployed | Jun 27, 2026 |
| M4 | Forecasting & Assistant Live | Sales dashboard and AI Assistant deployed | Aug 8, 2026 |
| M5 | Production Release | All features live, UAT passed, project closed | Sep 5, 2026 |

4.  Project Gantt Overview

| Weeks | Phase | Key Activities |
| --- | --- | --- |
| 1–2 | Discovery & Architecture | Audit, design, environment setup |
| 3–4 | Phase 2 | AI service layer, backend integration |
| 5–6 | Phase 2 | Lead scoring engine, frontend integration |
| 7–8 | Phase 3 | Rate analysis engine, quote recommendation |
| 9–10 | Phase 3 | Smart document generation |
| 11 | Phase 3 | Integration testing, bug fixes |
| 12–13 | Phase 4 | Forecasting model, dashboard development |
| 14–15 | Phase 4 | AI Assistant backend (query resolution) |
| 16–17 | Phase 4 | AI Assistant frontend, full integration testing |
| 18–19 | Phase 5 | UAT, refinement, security review |
| 20 | Phase 5 | Production deployment, handover, sign-off |

5.  Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Insufficient historical data for lead scoring model | Medium | High | Use hybrid rule-based + statistical approach as fallback |
| Claude API rate limits during peak usage | Low | Medium | Implement request queuing and response caching |
| Scope creep from additional stakeholder requests | Medium | High | Enforce formal change request process |
| UAT delays due to stakeholder availability | Medium | Medium | Schedule UAT sessions in advance; allow buffer weeks |
| Performance degradation from AI API latency | Low | Medium | Async processing; loading states in UI; response caching |

6.  Payment Schedule

|  | Payment Trigger | Amount (LKR) |
| --- | --- | --- |
| M0 | Signed agreement and scope approval (Project Kickoff) | LKR 104,000 (20%) |
| M2 | Client sign-off on Lead Scoring milestone | LKR 130,000 (25%) |
| M3 | Client sign-off on Quote & Document AI milestone | LKR 130,000 (25%) |
| M4 | Client sign-off on Forecasting & Assistant milestone | LKR 104,000 (20%) |
| M5 | Production deployment and handover complete (Final Sign-Off) | LKR 52,000 (10%) |
| TOTAL |  | LKR 520,000 |

7.  Communication Plan

| Type | Frequency | Channel |
| --- | --- | --- |
| Progress Update | Weekly | Email |
| Milestone Review | Per milestone | Meeting / Video call |
| Bug / Issue Reporting | As needed | Shared issue tracker |
| Final Presentation | End of project | On-site / Video call |

8.  Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Client Representative |  |  |  |
| Project Lead |  |  |  |